## Usage Guide
Hướng Dẫn Sử Dụng Agile Tracker - Sport Booking WebApp
Bước | Thời điểm | Sheet | Cần cập nhật | Cách sử dụng | Kết quả mong đợi
1 | Trước khi bắt đầu Sprint | Product Backlog | Priority, Target Sprint, Status, Owner, Story Points | Chọn các hạng mục sẽ làm và chuyển sang Ready hoặc To Do. Các hạng mục chưa rõ yêu cầu/API thì giữ ở Backlog. | Phạm vi Sprint rõ ràng, vừa sức và sẵn sàng thực hiện.
2 | Lập kế hoạch Sprint | Sprint Plan | Start Date, End Date, Status, Planned SP | Xác nhận mục tiêu Sprint, năng lực thực hiện và kịch bản demo. Không nhồi quá nhiều việc so với thời gian có thể làm. | Sprint có mục tiêu rõ và có kết quả demo đo được.
3 | Làm việc hằng ngày | Sprint Board | Status, Blocker, Next Action | Dùng sheet này như bảng công việc chính. Chuyển task từ To Do sang In Progress, Review, Done hoặc Blocked. | Trạng thái công việc hiện tại được nhìn thấy rõ.
4 | Khi hoàn thành task | Product Backlog + Sprint Board | Status | Chỉ đánh dấu Done sau khi đã kiểm tra backend/UI/thủ công theo Definition of Done. | Các chỉ số trên Dashboard tự động cập nhật.
5 | Trong quá trình phát triển | Risks | Impact, Probability, Mitigation, Status, Review Notes | Ghi rủi ro càng sớm càng tốt. Rủi ro có mức độ nghiêm trọng cao cần được xem lại trước demo Sprint. | Rủi ro được theo dõi trước khi biến thành blocker.
6 | Trước buổi demo | Demo Scripts | Status | Chạy đúng các bước demo đã ghi. Nếu flow bị lỗi, đánh dấu Blocked và ghi vấn đề vào notes/backlog. | Kết quả demo rõ ràng và có thể lặp lại.
7 | Trước khi deploy | Release Checklist | Status, Evidence / Link, Notes | Hoàn thành các mục Must trước. Evidence có thể là API collection, URL deploy, kết quả test hoặc mục trong README. | Bản demo production không phụ thuộc vào cấu hình local.
8 | Cuối Sprint | Dashboard | Chỉ xem lại | Kiểm tra số lượng backlog, task bị blocked, tiến độ release, rủi ro còn mở và trạng thái Sprint. | Sprint review dựa trên dữ liệu thật, không dựa vào cảm tính.
| Nguyên tắc quan trọng | Chi tiết |  | Trạng thái thường dùng | Ý nghĩa | Khi nào dùng
| Không đánh dấu Done quá sớm | Done nghĩa là code chạy được, API/UI đã được kiểm tra, quyền truy cập đã đúng và docs đã được cập nhật nếu cần. |  | Backlog | Chưa sẵn sàng hoặc chưa được chọn để làm | Ý tưởng, phạm vi tương lai hoặc hạng mục chưa rõ
| Giữ trạng thái nhất quán | Nếu một backlog item đã Done thì task liên quan trong Sprint Board cũng nên Done hoặc phải có lý do rõ ràng. |  | Ready | Đã đủ rõ để bắt đầu thực hiện | Docs/API/acceptance criteria đã rõ
| Luôn nghĩ theo hướng production | Tránh cấu hình chỉ chạy được ở localhost, hard-code secret hoặc thay đổi database thủ công không thể lặp lại. |  | To Do | Đã được chọn cho Sprint hiện tại | Việc trong Sprint nhưng chưa bắt đầu
| Mỗi Sprint phải demo được | Mỗi Sprint nên kết thúc bằng một flow thật có thể trình bày trên browser hoặc Postman. |  | In Progress | Đang được thực hiện | Developer đang code hoặc kiểm thử
| Ưu tiên task nhỏ | Nếu task lớn hơn 13 story points, nên tách thành backend, frontend, testing hoặc deployment task. |  | Review | Đã làm xong nhưng cần kiểm tra | Đang chờ test/review/demo check
| Cập nhật rủi ro hằng tuần | Rủi ro có severity cao cần có người phụ trách mitigation và hành động tiếp theo. |  | Done | Đạt Definition of Done | Đã kiểm tra và có thể sử dụng
|  |  |  | Blocked | Không thể tiếp tục nếu chưa xử lý vấn đề | Cần quyết định, dependency hoặc sửa lỗi
Phân biệt Product Backlog và Sprint Board
Sheet | Mục đích | Phạm vi | Ai dùng chính | Cập nhật khi nào | Ví dụ đúng
Product Backlog | Quản lý toàn bộ yêu cầu, feature, user story và technical item của cả dự án. | Toàn dự án: việc đang làm, sắp làm và có thể làm sau. | Product Owner, Developer | Khi thêm yêu cầu mới, đổi ưu tiên, chọn việc cho Sprint hoặc hoàn tất một backlog item. | PB-019: Implement booking creation with duplicate protection.
Sprint Board | Theo dõi các task cụ thể được tách ra từ backlog item trong Sprint. | Sprint hiện tại hoặc task đang cần theo dõi hằng ngày. | Developer, Tester | Cập nhật hằng ngày khi task chuyển To Do, In Progress, Review, Done hoặc Blocked. | SB-010 gắn Backlog ID = PB-019 để test duplicate booking.
Cách dùng đúng theo quy trình Sprint
Bước | Việc cần làm | Product Backlog | Sprint Board | Kết quả | Lưu ý
1 | Chuẩn bị Sprint | Chọn item ưu tiên cao, gán Target Sprint, chuyển Status sang Ready. | Chưa cần cập nhật hoặc chỉ tạo task nháp nếu chắc chắn. | Biết Sprint sắp làm backlog item nào. | Không chọn item chưa rõ acceptance criteria.
2 | Sprint Planning | Chốt item sẽ làm, có thể chuyển Status sang To Do. | Tạo task cụ thể và điền Backlog ID tương ứng. | Sprint có danh sách task rõ để bắt đầu. | Một backlog item có thể có nhiều task.
3 | Trong Sprint | Ít thay đổi, chỉ cập nhật nếu phạm vi hoặc trạng thái tổng thể đổi. | Cập nhật task hằng ngày: To Do, In Progress, Review, Done, Blocked. | Nhìn được tiến độ thật và blocker. | Không dùng Product Backlog thay cho board hằng ngày.
4 | Khi task xong | Chưa vội đánh dấu backlog item Done nếu các task liên quan chưa xong. | Đánh dấu task Done sau khi kiểm tra xong phần việc đó. | Sprint Board phản ánh tiến độ thật. | Task Done chưa chắc backlog item đã Done.
5 | Khi backlog item xong | Đánh dấu Done sau khi toàn bộ flow/API/UI/test đạt Definition of Done. | Các task liên quan nên Done hoặc có ghi chú rõ. | Dashboard cập nhật số Done chính xác. | Done theo giá trị sản phẩm, không chỉ theo số task.
6 | Cuối Sprint | Item chưa xong chuyển lại Backlog/Ready hoặc dời Target Sprint. | Task chưa xong chuyển Blocked/Moved hoặc tạo lại ở Sprint sau. | Sprint review và Sprint tiếp theo rõ ràng. | Không để task treo mà không có quyết định.

## Dashboard
Sport Booking WebApp - Agile Project Dashboard
Metric | Value | Sprint | Goal | Planned SP | Status | Demo
Backlog Items | 36 | Sprint 0 | Project foundation and production skeleton | 13 | Done | Backend/frontend run locally and health check works
Done Items | 6 | Sprint 1 | Database core and public browsing | 32 | Done | Guest browses courts from PostgreSQL data
In Progress Items | 0 | Sprint 2 | Local auth, JWT, refresh token, and profile | 37 | Planned | User registers, verifies, logs in, and views profile
Blocked Items | 0 | Sprint 3 | Vendor setup | 42 | Planned | Vendor prepares a bookable court
Release Checklist Done | 1/14 | Sprint 4 | Booking and cash payment MVP | 47 | Planned | User books by cash and vendor marks paid
Open Risks | 7 | Sprint 5 | VNPAY sandbox payment | 26 | Planned | User pays through VNPAY sandbox
|  | Sprint 6 | Admin dashboard and moderation | 34 | Planned | Admin moderates platform data
|  | Sprint 7 | Google login and UX polish | 21 | Planned | Google login and polished browsing flow
|  | Sprint 8 | Production hardening and release | 31 | Planned | Deployed production-like demo
Release Milestone | Included Through
MVP Alpha | Sprint 4 - public browsing, local auth, vendor setup, cash booking
MVP Beta | Sprint 6 - VNPAY sandbox, vendor booking, admin moderation
MVP Production Demo | Sprint 8 - deployment, demo data, README, smoke tests
Current Focus | Complete Sprint 0 before expanding scope
Rule | Working software over unfinished broad feature branches
Next Review | End of each sprint demo

## Product Backlog
ID | Epic | User Story / Task | Role | Priority | Target Sprint | Status | Owner | Story Points | Acceptance Criteria | Notes
PB-001 | Foundation | Initialize Spring Boot backend project | ADMIN | Must | Sprint 0 | Done | Developer | 3 | Backend starts locally and exposes health check
PB-002 | Foundation | Initialize React frontend with Tailwind CSS | Guest | Must | Sprint 0 | Done | Developer | 3 | Frontend starts locally at Vite dev URL
PB-003 | Foundation | Configure PostgreSQL and migration tooling | ADMIN | Must | Sprint 0 | Done | Developer | 5 | Migrations run successfully against PostgreSQL | Prefer Flyway or Liquibase
PB-004 | Foundation | Create README and environment examples | ADMIN | Must | Sprint 0 | Done | Developer | 2 | New developer can run project from README
PB-005 | Public Browsing | Create core entities and repositories | Guest | Must | Sprint 1 | Done | Developer | 8 | Tables match docs 04 and app starts without JPA errors
PB-006 | Public Browsing | Seed roles, sports, time slots, vendor, venues, and courts | Guest | Must | Sprint 1 | Done | Developer | 5 | Demo data appears after migration/seed
PB-007 | Public Browsing | Implement sports, venues, courts public APIs | Guest | Must | Sprint 1 | Review | Developer | 8 | APIs match docs 05 and return DTOs
PB-008 | Public Browsing | Build public court browsing pages | Guest | Must | Sprint 1 | Ready | Developer | 8 | Guest can browse courts from real API data
PB-009 | Auth | Implement local registration and email verification | USER | Must | Sprint 2 | Backlog | Developer | 8 | Unverified local account cannot log in
PB-010 | Auth | Implement login, JWT access token, refresh token rotation, logout | USER | Must | Sprint 2 | Backlog | Developer | 13 | Tokens work and old refresh token is revoked
PB-011 | Auth | Build login/register/profile frontend | USER | Must | Sprint 2 | Backlog | Developer | 8 | User can complete auth flow in browser
PB-012 | Auth | Implement avatar upload with shared storage service | USER | Must | Sprint 2 | Backlog | Developer | 5 | Avatar URL is saved to users.avatar_url
PB-013 | Vendor Setup | Implement vendor venue CRUD with ownership checks | VENDOR | Must | Sprint 3 | Backlog | Developer | 8 | Vendor can manage only own venues
PB-014 | Vendor Setup | Implement vendor court CRUD with ownership checks | VENDOR | Must | Sprint 3 | Backlog | Developer | 8 | Vendor can manage only courts under own venues
PB-015 | Vendor Setup | Implement venue and court image APIs | VENDOR | Must | Sprint 3 | Backlog | Developer | 8 | sortOrder and primary image rules are transactional
PB-016 | Vendor Setup | Implement court time slot configuration APIs | VENDOR | Must | Sprint 3 | Backlog | Developer | 5 | Vendor can enable/disable slots for own courts
PB-017 | Vendor Setup | Build vendor venue/court/image/slot UI | VENDOR | Must | Sprint 3 | Backlog | Developer | 13 | Vendor can prepare a bookable court from UI
PB-018 | Booking | Implement booking creation with duplicate protection | USER | Must | Sprint 4 | Backlog | Developer | 13 | Same court/date/slot cannot be double-booked
PB-019 | Booking | Implement available slots by court and date | USER | Must | Sprint 4 | Backlog | Developer | 5 | Only active and unbooked court slots are returned
PB-020 | Booking | Implement user booking history/detail/cancel APIs | USER | Must | Sprint 4 | Backlog | Developer | 8 | User can manage own bookings only
PB-021 | Booking | Implement vendor booking management and cash payment marking | VENDOR | Must | Sprint 4 | Backlog | Developer | 8 | Vendor can confirm/reject/cancel and mark cash paid
PB-022 | Booking | Build booking UI and vendor booking UI | USER | Must | Sprint 4 | Backlog | Developer | 13 | Cash-at-court booking can be demonstrated end to end
PB-023 | Payment | Implement VNPAY sandbox payment URL generation | USER | Must | Sprint 5 | Backlog | Developer | 8 | Booking with VNPAY returns a payment URL
PB-024 | Payment | Implement VNPAY return and IPN signature verification | USER | Must | Sprint 5 | Backlog | Developer | 13 | Invalid signature does not update payment
PB-025 | Payment | Build payment redirect/result frontend | USER | Must | Sprint 5 | Backlog | Developer | 5 | User sees clear payment result
PB-026 | Admin | Implement admin sports management | ADMIN | Must | Sprint 6 | Backlog | Developer | 5 | Admin can create/update/deactivate sports
PB-027 | Admin | Implement admin users/vendors management | ADMIN | Must | Sprint 6 | Backlog | Developer | 8 | Admin can manage user/vendor status and role
PB-028 | Admin | Implement admin venue/court/booking moderation | ADMIN | Must | Sprint 6 | Backlog | Developer | 8 | Admin can inspect and moderate platform data
PB-029 | Admin | Build admin dashboard pages | ADMIN | Must | Sprint 6 | Backlog | Developer | 13 | Admin flow can be demonstrated in UI
PB-030 | Auth | Implement Google login | USER | Should | Sprint 7 | Backlog | Developer | 8 | Verified Google email can log in | Clarify same-email local account behavior
PB-031 | UX | Improve responsive UI and empty/error states | Guest | Should | Sprint 7 | Backlog | Developer | 8 | Main pages work on desktop and mobile
PB-032 | UX | Add court filters by sport, venue, date, and keyword | Guest | Should | Sprint 7 | Backlog | Developer | 5 | Guest can narrow court list
PB-033 | Release | Prepare production config and deployment | ADMIN | Must | Sprint 8 | Backlog | DevOps | 8 | App deploys without localhost-only values
PB-034 | Release | Create production demo seed data and demo accounts | ADMIN | Must | Sprint 8 | Backlog | Developer | 5 | Demo environment has realistic data
PB-035 | Release | Add focused automated tests for risky logic | ADMIN | Should | Sprint 8 | Backlog | Tester | 13 | Auth, booking, ownership, image, payment rules are covered
PB-036 | Release | Finalize README, API notes, and smoke test checklist | ADMIN | Must | Sprint 8 | Backlog | Developer | 5 | Project is portfolio-ready

## Sprint Plan
Sprint | Goal | Start Date | End Date | Main Scope | Demo Scenario | Planned SP | Status
Sprint 0 | Project foundation and production skeleton | 2026-05-21 | 2026-05-22 | Backend, frontend, PostgreSQL, migrations, health check, README | Backend/frontend run locally and health check works | 13 | Done
Sprint 1 | Database core and public browsing | 2026-05-22 | 2026-05-23 | Entities, seed data, public sports/venues/courts APIs, public UI | Guest browses courts from PostgreSQL data | 32 | Done
Sprint 2 | Local auth, JWT, refresh token, and profile |  |  | Register, verify email, login, refresh, logout, profile, avatar | User registers, verifies, logs in, and views profile | 37 | Planned
Sprint 3 | Vendor setup |  |  | Vendor venues, courts, images, court time slots | Vendor prepares a bookable court | 42 | Planned
Sprint 4 | Booking and cash payment MVP |  |  | Available slots, booking, user history, vendor booking, cash payment | User books by cash and vendor marks paid | 47 | Planned
Sprint 5 | VNPAY sandbox payment |  |  | VNPAY payment URL, return, IPN, payment result UI | User pays through VNPAY sandbox | 26 | Planned
Sprint 6 | Admin dashboard and moderation |  |  | Sports, users/vendors, venues, courts, bookings admin UI | Admin moderates platform data | 34 | Planned
Sprint 7 | Google login and UX polish |  |  | Google login, responsive UI, filters, dashboard statistics | Google login and polished browsing flow | 21 | Planned
Sprint 8 | Production hardening and release |  |  | Prod config, seed demo data, tests, README, deployment | Deployed production-like demo | 31 | Planned

## Sprint Board
ID | Sprint | Task | Type | Priority | Status | Assignee | Owner | SP | Blocker | Next Action | Backlog ID | Note | Link
SB-001 | Sprint 0 | Create backend project and package structure | Backend | Must | Done | Dương Quốc Hiếu | Developer | 3 |  | Generate Spring Boot project | PB-001 |  | Pull Request #2
SB-011 | Sprint 0 | Define backend package structure by module | Backend | Must | Done | Dương Quốc Hiếu | Developer | 2 |  | Create packages for auth, user, sport, venue, court, booking, payment, common | PB-001 |  | Pull Request #2
SB-012 | Sprint 0 | Add health check controller | Backend | Must | Done | Dương Quốc Hiếu | Developer | 1 |  | Implement GET /api/health | PB-001 |  | Pull Request #2
SB-013 | Sprint 0 | Configure backend application profiles | Backend | Must | Done | Dương Quốc Hiếu | Developer | 2 |  | Create local and production-ready config structure | PB-001 |  | Pull Request #2
SB-002 | Sprint 0 | Create frontend project with Tailwind CSS | Frontend | Must | Done | Dương Quốc Hiếu | Developer | 3 |  | Create React app | PB-002 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/01c38b7f05e22696d4da7daecdea6255d82aa7ef
SB-014 | Sprint 0 | Configure React router and base layout | Frontend | Must | Done | Dương Quốc Hiếu | Developer | 2 |  | Create route skeleton and default layout | PB-002 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/1dc61b5806dd82d6278b16a77a670b1f2fafabaf
SB-015 | Sprint 0 | Configure Tailwind base theme | Frontend | Must | Done | Dương Quốc Hiếu | Developer | 1 |  | Set global styles and reusable layout classes | PB-002 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/68c7c7265f0f6bc84cbeba6ad132d0d5319c64a5
SB-016 | Sprint 0 | Create Axios API client skeleton | Frontend | Must | Done | Dương Quốc Hiếu | Developer | 2 |  | Add baseURL from environment variable | PB-002 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/e7f1cb3884c70e2631e7a305d47345e81d2386d5
SB-003 | Sprint 0 | Configure PostgreSQL and migrations | Database | Must | Done | Dương Quốc Hiếu | Developer | 5 |  | Choose Flyway or Liquibase | PB-003 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/9ea6710c55bd5d75ce992ff74a9f8bc98e625ef7
SB-017 | Sprint 0 | Choose and configure migration tool | Database | Must | Done | Dương Quốc Hiếu | Developer | 2 |  | Add Flyway or Liquibase dependency and config | PB-003 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/9ea6710c55bd5d75ce992ff74a9f8bc98e625ef7
SB-018 | Sprint 0 | Create initial database connection config | Database | Must | Done | Dương Quốc Hiếu | Developer | 2 |  | Use env variables for DB URL, username and password | PB-003 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/9ea6710c55bd5d75ce992ff74a9f8bc98e625ef7
SB-019 | Sprint 0 | Verify clean database startup | Test | Must | Done | Dương Quốc Hiếu | Tester | 1 |  | Run backend against empty PostgreSQL database | PB-003 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/9ea6710c55bd5d75ce992ff74a9f8bc98e625ef7
SB-004 | Sprint 0 | Add README setup draft | Docs | Must | Done | Dương Quốc Hiếu | Developer | 2 |  | Document local run commands | PB-004 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/ee452ebe7b0fe9bfb4b1f96c2503a23e0b9919da
SB-020 | Sprint 0 | Document local prerequisites | Docs | Must | Done | Dương Quốc Hiếu | Developer | 1 |  | Add Java, Node, PostgreSQL requirements to README | PB-004 |  | https://github.com/dqhieuse/sport_booking_webapp/pull/3
SB-021 | Sprint 0 | Document local backend and frontend run commands | Docs | Must | Done | Dương Quốc Hiếu | Developer | 1 |  | Add commands for backend, frontend and database | PB-004 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/ee452ebe7b0fe9bfb4b1f96c2503a23e0b9919da
SB-022 | Sprint 0 | Create environment example files | Docs | Must | Done | Dương Quốc Hiếu | Developer | 1 |  | Add backend and frontend env examples without secrets | PB-004 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/ee452ebe7b0fe9bfb4b1f96c2503a23e0b9919da
SB-023 | Sprint 1 | Create role and user entities | Database | Must | Done | Dương Quốc Hiếu | Developer | 3 |  | Implement mappings for roles and users | PB-005 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/a818783bc763e7894935b42c8907eccd84469495
SB-024 | Sprint 1 | Create sport, venue and court entities | Database | Must | Done | Dương Quốc Hiếu | Developer | 5 |  | Implement mappings and relationships from docs 04 | PB-005 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/0d1e65b2fe457df87125e1bd07cff1118089506a
SB-025 | Sprint 1 | Create image and time slot entities | Database | Must | Done | Dương Quốc Hiếu | Developer | 5 |  | Implement venue_images, court_images, time_slots, court_time_slots | PB-005 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/60c9e93ddd889fcf46afe0d050f85426039e38dd
SB-026 | Sprint 1 | Create repositories for core entities | Backend | Must | Done | Dương Quốc Hiếu | Developer | 3 |  | Add repository interfaces for public browsing entities | PB-005 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/ccc1d90b863917fa4444e3b3ed4a854c616c2da7
SB-027 | Sprint 1 | Seed roles and default sports | Database | Must | Done | Dương Quốc Hiếu | Developer | 2 |  | Seed USER, VENDOR, ADMIN and initial sports | PB-006 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/7c28081b592376b5f114320c4b2b97ab7aaafcf5
SB-028 | Sprint 1 | Seed global time slots | Database | Must | Done | Dương Quốc Hiếu | Developer | 2 |  | Add bookable time slot templates | PB-006 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/7c28081b592376b5f114320c4b2b97ab7aaafcf5
SB-029 | Sprint 1 | Seed demo vendor, venues and courts | Database | Must | Done | Dương Quốc Hiếu | Developer | 3 |  | Add realistic data for public browsing demo | PB-006 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/7c28081b592376b5f114320c4b2b97ab7aaafcf5
SB-005 | Sprint 1 | Implement public sports APIs | Backend | Must | Done | Dương Quốc Hiếu | Developer | 3 |  | Start after migrations | PB-007 | SB-030 covered by SB-005 commit | https://github.com/dqhieuse/sport_booking_webapp/commit/e970e163b1498ea48bb2a978c79ec2acc64e7493
SB-006 | Sprint 1 | Implement venue and court list/detail APIs | Backend | Must | Done | Dương Quốc Hiếu | Developer | 8 |  | Use DTOs | PB-007 | SB-031, SB-032 covered by SB-006 commit | https://github.com/dqhieuse/sport_booking_webapp/commit/e94d389dd5612f0c5334dca9f1a32a2ebfc7b484
SB-030 | Sprint 1 | Create sport response DTOs and service | Backend | Must | Done | Dương Quốc Hiếu | Developer | 2 |  | Return only necessary sport fields | PB-007 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/e970e163b1498ea48bb2a978c79ec2acc64e7493
SB-031 | Sprint 1 | Create venue list/detail DTOs and service | Backend | Must | Done | Dương Quốc Hiếu | Developer | 3 |  | Include primaryImageUrl in detail response | PB-007 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/505a5b2f4106a5681a9ae6920cd5f6778a43d28d
SB-032 | Sprint 1 | Create court list/detail DTOs and service | Backend | Must | Done | Dương Quốc Hiếu | Developer | 3 |  | Include sport, venue and primaryImageUrl | PB-007 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/6517f94dc54d956f2018cd3c7d5b40d10c88a7b4
SB-033 | Sprint 1 | Add public gallery APIs | Backend | Must | Done | Dương Quốc Hiếu | Developer | 2 |  | Implement venue and court image list APIs | PB-007 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/8450c708a287d7cceee8b9bbb48f2c7408861838
SB-007 | Sprint 1 | Build court list and detail pages | Frontend | Must | Done | Dương Quốc Hiếu | Developer | 8 |  | Connect to Axios client | PB-008 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/e56525bdc2a817c2e3725ffb2161949b3d2e3bd0
SB-034 | Sprint 1 | Create public home/discovery page | Frontend | Must | Done | Dương Quốc Hiếu | Developer | 3 |  | Show featured sports or courts from API | PB-008 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/f3874dedaafd79fa41468d446b09b3fcd230fcd8
SB-035 | Sprint 1 | Create court list page | Frontend | Must | Done | Dương Quốc Hiếu | Developer | 3 |  | Render courts from GET /courts | PB-008 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/8bfc111035aaeb6c025965253ca1464c2e08cf13
SB-036 | Sprint 1 | Create court detail page | Frontend | Must | Done | Dương Quốc Hiếu | Developer | 3 |  | Render court detail and image gallery link | PB-008 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/7bc4b76e12b9605a57605e02dad7bdf814952e71
SB-037 | Sprint 1 | Handle public browsing loading and error states | Frontend | Must | Done | Dương Quốc Hiếu | Developer | 2 |  | Show loading, empty and error UI | PB-008 |  | https://github.com/dqhieuse/sport_booking_webapp/commit/112c524ea170bd378a723c8489e3022b4ac2505a
SB-038 | Sprint 2 | Create email verification token entity and repository | Database | Must | Backlog |  | Developer | 3 |  | Map email_verification_tokens table | PB-009
SB-039 | Sprint 2 | Implement register local account API | Backend | Must | Backlog |  | Developer | 5 |  | Create USER with PENDING_VERIFICATION | PB-009
SB-040 | Sprint 2 | Implement verify email API | Backend | Must | Backlog |  | Developer | 3 |  | Activate account when valid token is used | PB-009
SB-041 | Sprint 2 | Implement resend verification API | Backend | Must | Backlog |  | Developer | 2 |  | Generate new token when account is not verified | PB-009
SB-008 | Sprint 2 | Implement auth security config | Backend | Must | Backlog |  | Developer | 8 |  | Define route permissions | PB-010
SB-009 | Sprint 2 | Implement token refresh flow in Axios | Frontend | Must | Backlog |  | Developer | 5 |  | Add interceptor | PB-010
SB-042 | Sprint 2 | Create refresh token entity and repository | Database | Must | Backlog |  | Developer | 3 |  | Store refresh token hash only | PB-010
SB-043 | Sprint 2 | Implement JWT access token service | Backend | Must | Backlog |  | Developer | 5 |  | Generate and validate access tokens | PB-010
SB-044 | Sprint 2 | Implement login API with email or phone | Backend | Must | Backlog |  | Developer | 5 |  | Block unverified local accounts | PB-010
SB-045 | Sprint 2 | Implement refresh token rotation | Backend | Must | Backlog |  | Developer | 5 |  | Revoke old refresh token and issue new token | PB-010
SB-046 | Sprint 2 | Implement logout API | Backend | Must | Backlog |  | Developer | 2 |  | Revoke submitted refresh token | PB-010
SB-047 | Sprint 2 | Build register page | Frontend | Must | Backlog |  | Developer | 3 |  | Call POST /auth/register and show verification message | PB-011
SB-048 | Sprint 2 | Build login page | Frontend | Must | Backlog |  | Developer | 3 |  | Support email/phone identifier | PB-011
SB-049 | Sprint 2 | Implement auth context and protected routes | Frontend | Must | Backlog |  | Developer | 5 |  | Protect user, vendor and admin routes | PB-011
SB-050 | Sprint 2 | Build profile page | Frontend | Must | Backlog |  | Developer | 2 |  | Render GET /auth/me data | PB-011
SB-051 | Sprint 2 | Create image storage service interface | Backend | Must | Backlog |  | Developer | 3 |  | Support local dev and future object storage | PB-012
SB-052 | Sprint 2 | Implement avatar upload validation | Backend | Must | Backlog |  | Developer | 3 |  | Validate file type and size | PB-012
SB-053 | Sprint 2 | Connect avatar upload UI | Frontend | Must | Backlog |  | Developer | 2 |  | Upload file and refresh profile avatar | PB-012
SB-054 | Sprint 3 | Implement vendor venue create/update APIs | Backend | Must | Backlog |  | Developer | 5 |  | Validate request and vendor ownership | PB-013
SB-055 | Sprint 3 | Implement vendor venue list/detail APIs | Backend | Must | Backlog |  | Developer | 3 |  | Return only venues owned by current vendor | PB-013
SB-056 | Sprint 3 | Implement vendor venue deactivate API | Backend | Must | Backlog |  | Developer | 3 |  | Prefer status change over hard delete | PB-013
SB-057 | Sprint 3 | Implement vendor court create/update APIs | Backend | Must | Backlog |  | Developer | 5 |  | Allow court only under owned venue | PB-014
SB-058 | Sprint 3 | Implement vendor court list/detail APIs | Backend | Must | Backlog |  | Developer | 3 |  | Return courts under vendor venues only | PB-014
SB-059 | Sprint 3 | Implement vendor court deactivate API | Backend | Must | Backlog |  | Developer | 3 |  | Protect existing booking history | PB-014
SB-060 | Sprint 3 | Implement venue image upload API | Backend | Must | Backlog |  | Developer | 5 |  | Apply sortOrder and primary image rules | PB-015
SB-061 | Sprint 3 | Implement court image upload API | Backend | Must | Backlog |  | Developer | 5 |  | Apply sortOrder and primary image rules | PB-015
SB-062 | Sprint 3 | Implement image delete and set primary APIs | Backend | Must | Backlog |  | Developer | 5 |  | Ensure only one primary image per venue/court | PB-015
SB-063 | Sprint 3 | Test image ordering transaction | Test | Must | Backlog |  | Tester | 3 |  | Verify insert at sortOrder shifts later images | PB-015
SB-064 | Sprint 3 | Implement global time slot list for vendor/admin | Backend | Must | Backlog |  | Developer | 2 |  | Return active time slot templates | PB-016
SB-065 | Sprint 3 | Implement get own court time slots API | Backend | Must | Backlog |  | Developer | 2 |  | Vendor can view enabled slots for own court | PB-016
SB-066 | Sprint 3 | Implement update own court time slots API | Backend | Must | Backlog |  | Developer | 3 |  | Update court_time_slots transactionally | PB-016
SB-067 | Sprint 3 | Build vendor venue management UI | Frontend | Must | Backlog |  | Developer | 5 |  | List, create, edit and deactivate venues | PB-017
SB-068 | Sprint 3 | Build vendor court management UI | Frontend | Must | Backlog |  | Developer | 5 |  | List, create, edit and deactivate courts | PB-017
SB-069 | Sprint 3 | Build vendor image gallery UI | Frontend | Must | Backlog |  | Developer | 5 |  | Upload, delete and set primary images | PB-017
SB-070 | Sprint 3 | Build court time slot configuration UI | Frontend | Must | Backlog |  | Developer | 3 |  | Enable and disable slots for court | PB-017
SB-010 | Sprint 4 | Test duplicate booking protection | Test | Must | Backlog |  | Tester | 5 |  | Verify same court/date/slot conflict | PB-019
SB-071 | Sprint 4 | Implement available slot query service | Backend | Must | Backlog |  | Developer | 5 |  | Calculate active and unbooked slots by date | PB-018
SB-072 | Sprint 4 | Add available slot API endpoint | Backend | Must | Backlog |  | Developer | 2 |  | Implement GET /courts/{id}/available-slots | PB-018
SB-073 | Sprint 4 | Test available slots with booked and disabled slots | Test | Must | Backlog |  | Tester | 3 |  | Verify unavailable slots are excluded | PB-018
SB-074 | Sprint 4 | Create booking and payment entities | Database | Must | Backlog |  | Developer | 5 |  | Map bookings and payments tables | PB-019
SB-075 | Sprint 4 | Implement booking creation transaction | Backend | Must | Backlog |  | Developer | 5 |  | Create booking and payment atomically | PB-019
SB-076 | Sprint 4 | Validate booking date and active court slot | Backend | Must | Backlog |  | Developer | 3 |  | Reject past date and disabled slot | PB-019
SB-077 | Sprint 4 | Add database-level duplicate booking protection | Database | Must | Backlog |  | Developer | 5 |  | Prevent duplicate active booking for court/date/slot | PB-019
SB-078 | Sprint 4 | Implement my bookings API | Backend | Must | Backlog |  | Developer | 3 |  | Return current user's bookings with payment summary | PB-020
SB-079 | Sprint 4 | Implement booking detail permission rules | Backend | Must | Backlog |  | Developer | 3 |  | User, vendor and admin access only valid bookings | PB-020
SB-080 | Sprint 4 | Implement user booking cancellation | Backend | Must | Backlog |  | Developer | 3 |  | Cancel valid future booking and update refund status if needed | PB-020
SB-081 | Sprint 4 | Implement vendor booking list filters | Backend | Must | Backlog |  | Developer | 3 |  | Filter by date, court and status | PB-021
SB-082 | Sprint 4 | Implement vendor confirm/reject/cancel booking APIs | Backend | Must | Backlog |  | Developer | 5 |  | Vendor can manage bookings for own courts only | PB-021
SB-083 | Sprint 4 | Implement mark cash payment as paid API | Backend | Must | Backlog |  | Developer | 3 |  | Only allow CASH_AT_COURT bookings | PB-021
SB-084 | Sprint 4 | Build available slot picker UI | Frontend | Must | Backlog |  | Developer | 5 |  | User selects date and available slot | PB-022
SB-085 | Sprint 4 | Build booking creation UI | Frontend | Must | Backlog |  | Developer | 5 |  | Submit booking with payment method | PB-022
SB-086 | Sprint 4 | Build booking history and detail UI | Frontend | Must | Backlog |  | Developer | 5 |  | User views booking history and detail | PB-022
SB-087 | Sprint 4 | Build vendor booking management UI | Frontend | Must | Backlog |  | Developer | 5 |  | Vendor confirms and marks cash paid | PB-022
SB-088 | Sprint 5 | Add VNPAY configuration properties | Backend | Must | Backlog |  | Developer | 3 |  | Load VNPAY config from environment variables | PB-023
SB-089 | Sprint 5 | Implement VNPAY payment URL builder | Backend | Must | Backlog |  | Developer | 5 |  | Generate signed sandbox payment URL | PB-023
SB-090 | Sprint 5 | Connect booking creation to VNPAY payment URL | Backend | Must | Backlog |  | Developer | 3 |  | Return paymentUrl for VNPAY bookings | PB-023
SB-091 | Sprint 5 | Implement VNPAY return endpoint | Backend | Must | Backlog |  | Developer | 5 |  | Verify return params and show result data | PB-024
SB-092 | Sprint 5 | Implement VNPAY IPN endpoint | Backend | Must | Backlog |  | Developer | 5 |  | Verify signature before updating payment | PB-024
SB-093 | Sprint 5 | Make VNPAY callback idempotent | Backend | Must | Backlog |  | Developer | 3 |  | Repeated callback should not corrupt payment status | PB-024
SB-094 | Sprint 5 | Test invalid VNPAY signature | Test | Must | Backlog |  | Tester | 3 |  | Invalid signature must not mark payment as paid | PB-024
SB-095 | Sprint 5 | Build payment redirect handling | Frontend | Must | Backlog |  | Developer | 3 |  | Redirect user to returned paymentUrl | PB-025
SB-096 | Sprint 5 | Build payment result page | Frontend | Must | Backlog |  | Developer | 2 |  | Show success, failed and pending result states | PB-025
SB-097 | Sprint 6 | Implement admin sport create/update APIs | Backend | Must | Backlog |  | Developer | 3 |  | Admin can create and update sports | PB-026
SB-098 | Sprint 6 | Implement admin sport deactivate API | Backend | Must | Backlog |  | Developer | 2 |  | Deactivate sport instead of hard delete | PB-026
SB-099 | Sprint 6 | Build admin sports management UI | Frontend | Must | Backlog |  | Developer | 3 |  | Admin can manage sports from UI | PB-026
SB-100 | Sprint 6 | Implement admin users/vendors list API | Backend | Must | Backlog |  | Developer | 3 |  | Support pagination and filters | PB-027
SB-101 | Sprint 6 | Implement admin user role/status update API | Backend | Must | Backlog |  | Developer | 5 |  | Admin can update role and account status | PB-027
SB-102 | Sprint 6 | Build admin users/vendors UI | Frontend | Must | Backlog |  | Developer | 5 |  | Admin can inspect and update accounts | PB-027
SB-103 | Sprint 6 | Implement admin venues moderation APIs | Backend | Must | Backlog |  | Developer | 3 |  | Admin can view and moderate venues | PB-028
SB-104 | Sprint 6 | Implement admin courts moderation APIs | Backend | Must | Backlog |  | Developer | 3 |  | Admin can view and moderate courts | PB-028
SB-105 | Sprint 6 | Implement admin bookings moderation APIs | Backend | Must | Backlog |  | Developer | 3 |  | Admin can view and moderate bookings | PB-028
SB-106 | Sprint 6 | Build admin dashboard summary | Frontend | Must | Backlog |  | Developer | 3 |  | Show basic platform summary cards | PB-029
SB-107 | Sprint 6 | Build admin venue/court moderation UI | Frontend | Must | Backlog |  | Developer | 5 |  | Admin can inspect and moderate venues/courts | PB-029
SB-108 | Sprint 6 | Build admin booking moderation UI | Frontend | Must | Backlog |  | Developer | 5 |  | Admin can inspect platform bookings | PB-029
SB-109 | Sprint 7 | Configure Google OAuth client | Backend | Should | Backlog |  | Developer | 2 |  | Load Google client ID from environment | PB-030
SB-110 | Sprint 7 | Implement Google ID token verification | Backend | Should | Backlog |  | Developer | 5 |  | Accept only verified Google emails | PB-030
SB-111 | Sprint 7 | Implement Google account matching behavior | Backend | Should | Backlog |  | Developer | 3 |  | Handle new email and existing local email cases | PB-030
SB-112 | Sprint 7 | Build Google login button flow | Frontend | Should | Backlog |  | Developer | 3 |  | Submit Google ID token to backend | PB-030
SB-113 | Sprint 7 | Review responsive layout on mobile | Frontend | Should | Backlog |  | Developer | 3 |  | Check public, auth, booking, vendor and admin pages | PB-031
SB-114 | Sprint 7 | Add reusable loading, empty and error components | Frontend | Should | Backlog |  | Developer | 3 |  | Use consistent states across pages | PB-031
SB-115 | Sprint 7 | Polish navigation by role | Frontend | Should | Backlog |  | Developer | 2 |  | Show relevant menu for guest/user/vendor/admin | PB-031
SB-116 | Sprint 7 | Add sport and venue filters to court list API | Backend | Should | Backlog |  | Developer | 3 |  | Support query params for sportId and venueId | PB-032
SB-117 | Sprint 7 | Add keyword and date filter support | Backend | Should | Backlog |  | Developer | 3 |  | Support keyword search and date-aware slot filtering if feasible | PB-032
SB-118 | Sprint 7 | Build court filter UI | Frontend | Should | Backlog |  | Developer | 3 |  | Allow user to filter by sport, venue, date and keyword | PB-032
SB-119 | Sprint 8 | Create production backend profile | Deployment | Must | Backlog |  | DevOps | 3 |  | Separate local and production settings | PB-033
SB-120 | Sprint 8 | Configure production frontend API URL | Deployment | Must | Backlog |  | DevOps | 2 |  | Use environment variable instead of localhost | PB-033
SB-121 | Sprint 8 | Prepare backend deployment steps | Deployment | Must | Backlog |  | DevOps | 3 |  | Document build and start command | PB-033
SB-122 | Sprint 8 | Prepare frontend deployment steps | Deployment | Must | Backlog |  | DevOps | 2 |  | Document production build and static hosting | PB-033
SB-123 | Sprint 8 | Create demo admin, vendor and user accounts | Database | Must | Backlog |  | Developer | 3 |  | Seed safe demo accounts | PB-034
SB-124 | Sprint 8 | Create realistic demo venues and courts | Database | Must | Backlog |  | Developer | 3 |  | Seed enough data for public browsing demo | PB-034
SB-125 | Sprint 8 | Create demo bookings and payments if safe | Database | Must | Backlog |  | Developer | 2 |  | Prepare useful dashboard and history data | PB-034
SB-126 | Sprint 8 | Add auth service tests | Test | Should | Backlog |  | Tester | 3 |  | Cover login, verification and refresh rotation | PB-035
SB-127 | Sprint 8 | Add booking conflict tests | Test | Should | Backlog |  | Tester | 3 |  | Cover duplicate booking and disabled slot | PB-035
SB-128 | Sprint 8 | Add vendor ownership tests | Test | Should | Backlog |  | Tester | 3 |  | Vendor cannot access other vendor data | PB-035
SB-129 | Sprint 8 | Add image ordering tests | Test | Should | Backlog |  | Tester | 2 |  | Validate sortOrder shift and primary image rule | PB-035
SB-130 | Sprint 8 | Add payment callback tests | Test | Should | Backlog |  | Tester | 2 |  | Validate signature and idempotency behavior | PB-035
SB-131 | Sprint 8 | Finalize README local setup section | Docs | Must | Backlog |  | Developer | 2 |  | Document local backend, frontend and database setup | PB-036
SB-132 | Sprint 8 | Finalize README production deployment section | Docs | Must | Backlog |  | Developer | 2 |  | Document environment variables and deployment steps | PB-036
SB-133 | Sprint 8 | Create API testing or Postman notes | Docs | Must | Backlog |  | Tester | 2 |  | Document how to test core APIs | PB-036
SB-134 | Sprint 8 | Create production smoke test checklist | Docs | Must | Backlog |  | Tester | 2 |  | Document browse, login, booking, vendor and admin checks | PB-036

## Release Checklist
Area | Checklist Item | Priority | Status | Evidence / Link | Notes
Configuration | All secrets are environment variables | Must | Done |  | JWT, DB, Google, VNPAY, storage
Database | Migrations run from clean database | Must | Not Started |  | No manual table creation
Database | Demo seed data exists | Must | Not Started |  | Admin, vendor, user, sports, venues, courts
Security | Protected APIs reject missing/invalid token | Must | Not Started
Security | Role-based routes are enforced in backend | Must | Not Started
Security | Vendor ownership checks are verified | Must | Not Started
Auth | Refresh token rotation works | Must | Not Started
Booking | Duplicate booking is blocked | Must | Not Started
Payment | VNPAY invalid signature is rejected | Must | Not Started
Frontend | Production build succeeds | Must | Not Started
Frontend | Frontend uses deployed backend URL | Must | Not Started
Docs | README has local and production run instructions | Must | Not Started
Demo | Smoke test script passes on deployed app | Must | Not Started
Observability | Backend logs are useful for demo debugging | Should | Not Started

## Risks
ID | Risk | Impact (1-5) | Probability (1-5) | Severity | Mitigation | Owner | Status | Review Notes
R-001 | Frontend is built too late, making demo weak | 4 | 4 | 16 | Build UI together with each vertical slice | Product Owner | Open
R-002 | VNPAY takes longer than expected | 4 | 3 | 12 | Finish CASH_AT_COURT booking before VNPAY | Developer | Open
R-003 | Auth scope becomes too complex | 5 | 3 | 15 | Finish local auth first, then Google login | Developer | Open
R-004 | Image storage complicates deployment | 3 | 3 | 9 | Use storage abstraction and start simple | Developer | Open
R-005 | No migration strategy causes deployment issues | 5 | 2 | 10 | Use Flyway or Liquibase from Sprint 0 | Developer | Open
R-006 | Weak seed data makes demo look empty | 3 | 4 | 12 | Prepare realistic demo venues, courts, slots, bookings | Product Owner | Open
R-007 | Missing ownership checks exposes vendor data | 5 | 3 | 15 | Put checks in service layer and test them | Tester | Open

## Demo Scripts
Flow | Actor | Sprint | Steps | Expected Result | Status
Public browsing | Guest | Sprint 1 | Open app > view sports > open court list > open court detail | Guest sees real court data and primary images | Not Started
Local auth | USER | Sprint 2 | Register > verify email > login > open profile > logout | User receives tokens and protected profile loads | Not Started
Vendor court setup | VENDOR | Sprint 3 | Login as vendor > create venue > create court > upload image > enable slots | Court becomes bookable | Not Started
Cash booking | USER/VENDOR | Sprint 4 | User books CASH_AT_COURT > vendor confirms > vendor marks cash paid | Booking and payment statuses update correctly | Not Started
VNPAY payment | USER | Sprint 5 | User books with VNPAY > completes sandbox payment > returns to app | Payment status becomes PAID | Not Started
Admin moderation | ADMIN | Sprint 6 | Login as admin > manage sport > inspect users > moderate court/booking | Admin can manage platform data | Not Started
Production smoke test | All | Sprint 8 | Run core flow on deployed URL | Demo environment works without localhost assumptions | Not Started

## Lookups
Status | Priority | Owner | Role | Type | Sprint Status | Release Status | Risk Status | Members
Backlog | Must | Developer | Guest | Backend | Not Started | Not Started | Open | Dương Quốc Hiếu
Ready | Should | Product Owner | USER | Frontend | Planned | In Progress | Monitoring
To Do | Could | Tester | VENDOR | Database | In Progress | Done | Mitigated
In Progress | Won't | Designer | ADMIN | Test | Done | Blocked | Closed
Review |  | DevOps |  | Docs | At Risk | Deferred | Accepted
Done |  |  |  | Deployment | Moved | N/A
Blocked